## Slide 1: MAZE RUNNER

## Slide 2: Virtual reality, a new frontier
What
Why
Huh

## Slide 3: Meet the Team
IT Manager: Jacob
Software Architect: Cameron
Quality Assurance Manager: Conrad
Project Manager: Benjamin
Coding Standards: Delaney
Documentation Specialist: Corbin

## Slide 4: Global Use Case

## Slide 5: Context Diagram

## Slide 6: Project breakdown Diagram
Team Member | Subsystem
Jacob | Level Design
Ben | Player Management
Cameron | Menu Management
Cameron | Sound Management
Corbin | Enemy Management
Delaney | Item Management
Conrad | Score Management

## Slide 7: Level Design
Priority Level: 1
Role:
Load all game assets properly into the world
  Player
  Items
  Enemies
  World assets
Bounds check all game assets
Raise collision flags on player collision with map assets
Swap scenes

## Slide 8: Level Design

## Slide 9: Level Design
Task​ | Duration (PWks)​ | Predecessor Task(s)​
1. Obtain 3D assets | 1​ | -​
2. Implement World loading | 2​ | 1​
3. Implement Item/Player/Enemy loading | 3 | 2​
4. Implement Bounds Check​ | 2​ | 3​
5. Implement Player manager Collision Check​ | 1​ | 3​
6. Implement scene swapper | 1 | 2
7. Testing | 2 | 6
8. Installation | 1 | 7

## Slide 10: Level Design
Questions?

## Slide 11: Player Management
Priority Level: 1
Role:
To receive direct input from the user to streamline the process
Responsible for moving the player and checking its possible updated position using collision checks
Ensuring the player’s movements are smooth, they cannot travel out of bounds, and that collision detection works

## Slide 12: Player Management

## Slide 13: Player Management
Task | Duration (PWks) | Predecessor Task(s)
1. Requirements Collection | 1 | -
2. Implement Manage Player Controls | 2 | 1
3. Implement Update Player Position | 2 | 2
4. Implement Collision Check | 2 | 3
5. Implement Item Collision Check | 1 | 3
6. Testing | 2 | 5
7. Installation | 1 | 6

## Slide 14: Player Management
Questions?

## Slide 15: Player Management
Questions?

## Slide 16: Enemy Management
Priority Level: 2
Role:
Control the spawning and despawning of enemies in the game
Keep track of all enemies' stats such as health, damage, is spawned... etc
Manage the movement of each enemy in the game
Manage the interactions between enemies and certain items in the game
Manage combat between enemies and the player

## Slide 17: Enemy Management

## Slide 18: Enemy Management
Task​ | Duration (PWks)​ | Predecessor Task(s)​
1. Requirements Collection​ | 1​ | -​
2. Prototype Design​ | 1​ | 1​
3. Enemy Spawning​ | 1​ | 2​
4. Enemy Movement​ | 3​ | 3​
5. Enemy Item Interactions​ | 2​ | 4​
6. Enemy Combat System​ | 2​ | 4​
7. Testing​ ​ | 3​ | 5,6​

## Slide 19: Enemy Management
Questions?

## Slide 20: Item Management
Priority Level:
Role:

## Slide 21: Item Management
Task​​ | Duration (PWks)​​ | Predecessor Task(s)​​
1. Requirements Collection​​ | 3 | -​​
2. ​​Function Definitions | 2 | 1​​
3. ​​User Documentation | 1 | 1
4. Programming | 3​​ | 2,3​​
5. Testing | 2​​ | 4​​
6. Installation | 2​​ | 5​​

## Slide 22: Menu Management
Priority Level: 3
Role of the Menu:
  Take user input and translate that into something the game can use
  Create a customizeable/unique user experience

## Slide 23: Menu Management

## Slide 24: Menu Management
Task | Duration (PHrs) | Predecessor Task(s)
1. Define Settings | 1 | -
2. Menu Layout | 1 | 1
3. Create Main Menu | 5 | 1,2
4. Create Scene Switcher | 1 | 3
5. Create Buttons | 6 | 3
6. Create Options Menu | 18 | 3
7. Testing | 6 | 3,6
8. Installation | 8 | 7

## Slide 25: Menu Management
Questions?

## Slide 26: Sound Management
Role: Provide auditory sensory to player to construct a more powerful Virtual Reality Experience
Priority: 3
no other systems depend on this mechanism, but we value it as an essential feature

## Slide 27: Sound Management
Sounds and Music rely on a Trigger Event

## Slide 28: Sound Management
Task | Duration | Predecessor Task(s)
1. Event Decoding | 1 | 5
2. Sound Control | 1 | -
3. Music Control | 1 | 2
4. Testing | 2 | 1, 3
5. Asset Collection | 2 | -
6. Final Merge | 1 | 4

## Slide 29: Menu Management
Questions?

## Slide 30: Overall Questions?