## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Jacob: | 2700 | 525 | 2175 | 100 | 50 | 50 | 1500 | 475 | 1025 | 1100 | 0 | 1100
Cameron: | 2600 | 475 | 2125 | 0 | 0 | 0 | 1500 | 475 | 1025 | 1100 | 0 | 1100
Conrad: | 2600 | 525 | 2075 | 0 | 0 | 0 | 1500 | 525 | 975 | 1100 | 0 | 1100
Benjamin: | 2750 | 825 | 1925 | 150 | 150 | 0 | 1500 | 525 | 975 | 1100 | 150 | 950
Delaney: | 2700 | 725 | 1975 | 100 | 200 | -100 | 1500 | 525 | 975 | 1100 | 0 | 1100
Corbin: | 2700 | 545 | 2155 | 100 | 20 | 80 | 1500 | 525 | 975 | 1100 | 0 | 1100
Totals: | 16050 | 3620 | 12430 | 450 | 420 | 30 | 9000 | 3050 | 5950 | 6600 | 150 | 6450

## Gantt
| Time Predicted (hrs) | Time Spent (hrs) | Key | Completed | This Week | Planned
Jacob: |  |  | Hours:
GitHub and Discord Setup | 1 | 0.5
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 0.5
Cameron: |  |  | Hours:
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 0 | 0
Conrad: |  |  | Hours:
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 0 | 0
Benjamin: |  |  | Hours:
Setup Master Gantt | 1 | 1
Creating Shared Documents and Organizing Workload | 0.5 | 0.5
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1.5 | 1.5
Delaney: |  |  | Hours:
Coding Standards | 1 | 2
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 2
Corbin: |  |  | Hours:
Logo Design | 1 | 0.2
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 0.2
group totals (hrs) | 4.5 | 4.2
group totals ($) | 450 | 420

## Meetings
ü | Date: | Jan. 25 | Jan. 28 | Jan. 29 | Jan. 31 | TBD | TBD | TBD | TBD | TBD | TBD
| Purpose: | Meeting the Team | RFP and SA Presentation Breakdown | Assigned RFP Sections | Worked through RFP and SA Presentations | TDB | TDB | TDB | TBD | TBD | TBD
| Hours: | 1.5 | 0.5 | 0.25 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Jacob: | 4.75 | ü |  | ü | ü
Cameron: | 4.75 | ü |  | ü | ü
Conrad: | 5.25 | ü | ü | ü | ü
Benjamin: | 5.25 | ü | ü | ü | ü
Delaney: | 5.25 | ü | ü | ü | ü
Corbin: | 5.25 | ü | ü | ü | ü
Totals: | 30.5 | 9 | 2 | 1.5 | 18 | 0 | 0 | 0 | 0 | 0 | 0

## SA
| Task: (RED IS DEPENDENT ON OTHERS) | Time Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Jacob: | Champion (Map) | 6 | 0
| RFP (1 & 2) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Cameron: | Champion (Menu & Sound) | 6 | 0
| RFP (7) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Conrad: | Champion (Score) | 6 | 0
| RFP (5 & 6) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Benjamin: | Champion (Player) | 6 | 0
| RFP (9) | 3 | 1.5
| SA Presentation | 2 | 0
| Subtotal | 11 | 1.5
Delaney: | Champion (Items) | 6 | 0
| RFP (8 & 10) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Corbin: | Champion (Enemies) | 6 | 0
| RFP (3 & 4) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal: | 11 | 0
| Totals: | 66 | 1.5