## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Jacob: | 2700 | 925 | 1775 | 100 | 50 | 50 | 1500 | 875 | 625 | 1100 | 0 | 1100
Cameron: | 2600 | 1675 | 925 | 0 | 0 | 0 | 1500 | 875 | 625 | 1100 | 800 | 300
Conrad: | 2600 | 925 | 1675 | 0 | 0 | 0 | 1500 | 925 | 575 | 1100 | 0 | 1100
Benjamin: | 5700 | 1875 | 3825 | 3100 | 100 | 3000 | 1500 | 925 | 575 | 1100 | 850 | 250
Delaney: | 2700 | 1125 | 1575 | 100 | 200 | -100 | 1500 | 925 | 575 | 1100 | 0 | 1100
Corbin: | 2700 | 2395 | 305 | 100 | 20 | 80 | 1500 | 925 | 575 | 1100 | 1450 | -350
Totals: | 19000 | 8920 | 10080 | 3400 | 370 | 3030 | 9000 | 5450 | 3550 | 6600 | 3100 | 3500

## Gantt
| Time Predicted (hrs) | Time Spent (hrs) | Key | Completed | This Week | Planned
Jacob: |  |  | Hours:
GitHub and Discord Setup | 1 | 0.5
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 0.5
Cameron: |  |  | Hours:
Plan Menus | 0 | 0
Create Menus | 0 | 0
Create Buttons | 0 | 0
Collect Sounds | 0 | 0
Make stuff work together | 0 | 0
Testing | 0 | 0
Installation | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 0 | 0
Conrad: |  |  | Hours:
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 0 | 0
Benjamin: |  |  | Hours:
Setup Master Gantt | 1 | 1
Requirements Collection | 3 | 0
Implement Manage Player Controls | 6 | 0
Implement Update Player Position | 6 | 0
Implement Collision Check | 6 | 0
Implement Item Collision Check | 3 | 0
Testing | 4 | 0
Instalation | 2 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 31 | 1
Delaney: |  |  | Hours:
Coding Standards | 1 | 2
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 2
Corbin: |  |  | Hours:
Logo Design | 1 | 0.2
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 1 | 0.2
group totals (hrs) | 34 | 3.7
group totals ($) | 3400 | 370

## Meetings
ü | Date: | Jan. 25 | Jan. 28 | Jan. 29 | Jan. 31 | Feb. 5 | Feb. 6 | TBD | TBD | TBD | TBD
| Purpose: | Meeting the Team | RFP and SA Presentation Breakdown | Assigned RFP Sections | Worked through RFP and SA Presentation | Finished Champions, RFP, and SA Presentation | Presentation Rehersal | TDB | TBD | TBD | TBD
| Hours: | 1.5 | 0.5 | 0.25 | 3 | 2.5 | 1.5 | 0 | 0 | 0 | 0
Jacob: | 8.75 | ü |  | ü | ü | ü | ü
Cameron: | 8.75 | ü |  | ü | ü | ü | ü
Conrad: | 9.25 | ü | ü | ü | ü | ü | ü
Benjamin: | 9.25 | ü | ü | ü | ü | ü | ü
Delaney: | 9.25 | ü | ü | ü | ü | ü | ü
Corbin: | 9.25 | ü | ü | ü | ü | ü | ü
Totals: | 54.5 | 9 | 2 | 1.5 | 18 | 15 | 9 | 0 | 0 | 0 | 0

## SA
| Task: (RED IS DEPENDENT ON OTHERS) | Time Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Jacob: | Champion (Map) | 6 | 0
| RFP (1 & 2) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Cameron: | Champion (Menu & Sound) | 6 | 6
| RFP (7) | 3 | 1
| SA Presentation | 2 | 1
| Subtotal | 11 | 8
Conrad: | Champion (Score) | 6 | 0
| RFP (5 & 6) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Benjamin: | Champion (Player) | 6 | 5
| RFP (9) | 3 | 1.5
| SA Presentation | 2 | 2
| Subtotal | 11 | 8.5
Delaney: | Champion (Items) | 6 | 0
| RFP (8 & 10) | 3 | 0
| SA Presentation | 2 | 0
| Subtotal | 11 | 0
Corbin: | Champion (Enemies) | 6 | 12
| RFP (3 & 4) | 3 | 0.5
| SA Presentation | 2 | 2
| Subtotal: | 11 | 14.5
| Totals: | 66 | 31