## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Jacob: | 7100 | 7975 | -875 | 4300 | 4750 | -450 | 1500 | 2025 | -525 | 1300 | 1200 | 100
Cameron: | 2600 | 3025 | -425 | 0 | 0 | 0 | 1500 | 2225 | -725 | 1100 | 800 | 300
Conrad: | 4500 | 3225 | 1275 | 1900 | 800 | 1100 | 1500 | 2425 | -925 | 1100 | 0 | 1100
Benjamin: | 7500 | 6375 | 1125 | 4500 | 2800 | 1700 | 1500 | 2425 | -925 | 1500 | 1150 | 350
Delaney: | 7400 | 4275 | 3125 | 4500 | 600 | 3900 | 1500 | 2275 | -775 | 1400 | 1400 | 0
Corbin: | 7000 | 5345 | 1655 | 4000 | 920 | 3080 | 1500 | 2275 | -775 | 1500 | 2150 | -650
Totals: | 36100 | 30220 | 5880 | 19200 | 9870 | 9330 | 9000 | 13650 | -4650 | 7900 | 6700 | 1200

## Gantt
| Time Predicted (hrs) | Time Spent (hrs) | Key | Completed | This Week | Planned
Jacob: |  |  | Hours:
GitHub and Discord Setup | 1 | 0.5
Obtain 3D Assets | 5 | 10
Implement World Loading | 3 | 4
Implement Bounds Check | 15 | 10
Implement item/playe/enemie loading | 10 | 20
Implement Player manager collision | 2 | 1
Implement Scene Swapper | 1 | 2
Testing | 5 | 0
Instalation | 1 | 0
TBD | 0 | 0
Totals: | 43 | 47.5
Cameron: |  |  | Hours:
Plan Menus | 0 | 0
Create Menus | 0 | 0
Create Buttons | 0 | 0
Collect Sounds | 0 | 0
Make stuff work together | 0 | 0
Testing | 0 | 0
Installation | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 0 | 0
Conrad: |  |  | Hours:
VR Integration and Setup | 2 | 2
Sound | 3 | 0
Enemy Testing | 1 | 1
Item Integration | 2 | 4
Maze Testing | 3 | 0
Auto-Tester | 4 | 1
Integrate Tests | 2 | 0
Refactor Asset Organization | 2 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 19 | 8
Benjamin: |  |  | Hours:
Setup Master Gantt | 1 | 1
Requirements Collection | 3 | 2.5
Implement Manage Player Controls | 6 | 5.5
Implement Update Player Position | 6 | 7
Implement Player Health | 4 | 4
Implement Collision Check | 6 | 6
Implement Item Collision Check | 3 | 2
Implement Dynamic Binding and Paterns | 6 | 0
Testing | 8 | 0
Instalation | 2 | 0
Totals: | 45 | 28
Delaney: |  |  | Hours:
Coding Standards | 1 | 2
Requirements Collection | 3 | 3
Implement Item-Player interaction | 6 | 1
Implement Item Placement | 3 | 0
Implement Item-Enemy interaction | 6 | 0
End Game Trigger | 2 | 0
Testing | 7 | 0
Integration | 3 | 0
TBD | 0 | 0
TBD | 0 | 0
Totals: | 45 | 6
Corbin: |  |  | Hours:
Logo Design | 1 | 0.2
Requirements Collection | 3 | 3
Prototype Design | 4 | 2
Enemy Spawning | 3 | 2
Enemy Movement | 6 | 2
Enemy Item Interaction | 4 | 0
Enemy Combat System | 4 | 0
Testing | 10 | 0
Create Game Guide | 5 | 0
TBD | 0 | 0
Totals: | 40 | 9.2
group totals (hrs) | 192 | 98.7
group totals ($) | 19200 | 9870

## Meetings
ü | Date: | Jan. 25 | Jan. 28 | Jan. 29 | Jan. 31 | Feb. 5 | Feb. 6 | Mar. 19 | Mar. 25 | Mar. 28 | Apr. 2-3
| Purpose: | Meeting the Team | RFP and SA Breakdown | Assigned RFP Sections | Worked through RFP and SA Presentation | Finished Champions, RFP, and SA Presentation | Presentation Rehersal | Stress Testing and Progress Check | Player Additions | Master Merge and Progress Check | Testing
| Hours: | 1.5 | 0.5 | 0.25 | 3 | 2.5 | 1.5 | 3.5 | 1.5 | 4 | 6
Jacob: | 20.25 | ü |  | ü | ü | ü | ü |  | ü | ü | ü
Cameron: | 22.25 | ü |  | ü | ü | ü | ü | ü |  | ü | ü
Conrad: | 24.25 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Benjamin: | 24.25 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Delaney: | 22.75 | ü | ü | ü | ü | ü | ü | ü |  | ü | ü
Corbin: | 22.75 | ü | ü | ü | ü | ü | ü | ü |  | ü | ü
Totals: | 136.5 | 9 | 2 | 1.5 | 18 | 15 | 9 | 17.5 | 4.5 | 24 | 36

## SA
| Task: | Time Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Jacob: | Champion (Map) | 6 | 7 | bar: 1 to 6
| RFP (1 & 2) | 3 | 1 | bar: 1 to 3
| SA Presentation | 2 | 2 | bar: 7 to 8
| Class Diagram | 1 | 1 | bar: 8
| Sequence Diagram | 1 | 1 | bar: 8
| Subtotal | 13 | 12
Cameron: | Champion (Menu & Sound) | 6 | 6 | bar: 10 to 11
| RFP (7) | 3 | 1 | bar: 8 to 9
| SA Presentation | 2 | 1 | bar: 6 to 7
| Class Diagram | 0 | 0 | bar: 1 to 2
| Sequence Diagram | 0 | 0 | bar: 1 to 2
| Subtotal | 11 | 8
Conrad: | Champion (Score) | 6 | 0
| RFP (5 & 6) | 3 | 0
| SA Presentation | 2 | 0
| Class Diagram | 0 | 0
| Sequence Diagram | 0 | 0
| Subtotal | 11 | 0
Benjamin: | Champion (Player) | 6 | 5 | bar: 4 to 9
| RFP (9) | 3 | 1.5 | bar: 1 to 3
| SA Presentation | 2 | 2 | bar: 10 to 11
| Class Diagram | 2 | 1.5 | bar: 10 to 11
| Sequence Diagram | 2 | 1.5 | bar: 10 to 11
| Subtotal | 15 | 11.5
Delaney: | Champion (Items) | 6 | 6 | bar: 1 to 6
| RFP (8 & 10) | 3 | 1 | bar: 1
| SA Presentation | 2 | 2 | bar: 7 to 8
| Class Diagram | 2 | 3 | bar: 9 to 11
| Sequence Diagram | 1 | 2 | bar: 12 to 13
| Subtotal | 14 | 14
Corbin: | Champion (Enemies) | 6 | 12 | bar: 1 to 12
| RFP (3 & 4) | 3 | 0.5 | bar: 13
| SA Presentation | 2 | 2 | bar: 14 to 15
| Class Diagram | 2 | 4 | bar: 16 to 20
| Sequence Diagram | 2 | 3 | bar: 21 to 23
| Subtotal: | 15 | 21.5
| Totals: | 79 | 67